San Bernardino Community College District

District Strategic Planning Committee

Task Schedule, 2010-11

Approved by Consensus, September 10, 2010

Notes

- Discussion and action on a given item normally require that the material to be discussed be distributed well before the applicable meeting.  Deadlines for preparation of materials should be set accordingly.

- It is likely that this schedule will require adjustments over the course of the year.

| Meeting | Major Tasks |
| --- | --- |
| August 27, 2010 | Implementation kickoff Initial meeting with all point persons |
| September 10 | Establishment of priorities for implementation of objectives (with resources where requested) Review and discussion of District foundational statements, with possible action on revision process (to be merged into this task schedule) Discussion of integration of KVCR and EDCT into DSP Designation of member(s) or subcommittee(s) to make recommendations on integration of KVCR and EDCT into DSP (process to be merged into this task schedule) |
| September 24 | Discussion of and recommendations on additional input and feedback mechanisms Designation of subcommittee(s) and schedule for implementation of additional mechanisms, if needed Review and discussion of existing research, and identification of information needs for exemplary DSP. Designation of subcommittee(s) to spearhead fulfillment of information needs for DSP |
| October 8 | Review and discussion of strategic issues, including possible additions Designation of subcommittees to prepare updates/reports on strategic issues |
| October 22 | Designation of editing subcommittee, charged with preparation of DSP drafts Subcommittee reports. |
| November 5 | Subcommittee reports. |
| November 19 | Subcommittee reports. |
| December 10 | Review, discussion, and possible action on first quarterly reports (due Dec. 3) Subcommittee reports. |
| January 28, 2011 | Subcommittee reports. |
| February 18 | Reminder through presidents to major college committees requesting reports on progress related to DSP goals and objectives by March 11. Request for other progress reports by March 11: On DTSP from DETS Executive Committee On Staffing Plan from Human Resources Department On Resource Allocation Model from District Budget Committee Subcommittee reports. Review and discussion of planning assumptions in light of all information received to date Review and discussion of DSP evaluation and revision provisions, followed by modifications as needed |
| March 4 | Review, discussion, and possible action on second quarterly reports (due Feb. 26) Final revision of planning assumptions as needed Initial review of Strategic Directions, Goals, Objectives, Actions, measurements, timelines, and point persons for possible modifications, additions, or retirements |
| March 18 | Review and discussion of college committee progress reports Review and discussion of other progress reports Discussion and documentation of alignment with college and other strategic plans Review and discussion of first full draft of revised DSP, followed by modifications as needed Schedule of forums or presentations on revised DSP during week of April 4 |
| April 1 | Second review of Strategic Directions, Goals, Objectives, Actions, measurements, timelines, and point persons for possible modifications, additions, or retirements Approval of draft revised DSP for feedback distribution; distribution of draft to follow immediately with response deadline of April 8-11 |
| April 15 | Review and incorporation of feedback into revised DSP as appropriate Review and discussion of glossary, with possible additions or modifications |
| April 29 | Review, discussion, and possible action on third quarterly reports (due April 22) |
| May 13 | Final recommendation on revised DSP, to be forwarded to the Chancellor and then to the Board for approval |

# Text boxes

3A